## COVID-19 Preparedness Plan - Pu
Goals and Objectives | Start Date | Target Completion Date | Assigned To | Status
1. Assemble a COVID communication / response team
a) Leadership Team | 2020-03-18 | 2020-04-03 |  | In progress
b) Exco / Board as needed | 2020-03-18 | 2020-04-03 |  | In progress
c) Team Meet / Conference kick off call | 2020-03-18 | 2020-04-03 |  | In progress
2. Member Communication
a) Member Email #1 | 2020-03-18 | 2020-04-03 |  | Complete
Message Compose - We are aware | 2020-03-18 | 2020-04-03 |  | Complete
b) Member Email #2 | 2020-03-18 | 2020-04-03 |  | In progress
Message - Club Closed till _________ | 2020-03-18 | 2020-04-03 |  | In progress
c) Member Email #3 | 2020-03-18 | 2020-04-03 |  | Not Started
Message - Pick up reminder | 2020-03-18 | 2020-04-03 |  | Not Started
d) President's Message | 2020-03-18 | 2020-04-03 |  | Not Started
Message - Pick up reminder | 2020-03-18 | 2020-04-03 |  | Not Started
3. Staff Communication
a) Hiring Freeze in effect till further notice | 2020-03-18 | 2020-04-03 |  | Not Started
b) Determine what we can and can’t do legally - seek legal advice | 2020-03-18 | 2020-04-03 |  | Not Started
c) Families Care Act | 2020-03-18 | 2020-04-03 |  | Not Started
Payroll taxes relief | 2020-03-18 | 2020-04-03 |  | Not Started
Sick pay policy change | 2020-03-18 | 2020-04-03 |  | Not Started
FMLA assistance | 2020-03-18 | 2020-04-03 |  | Not Started
d) Staff Emails | 2020-03-18 | 2020-04-03 |  | Not Started
4. Exco/ Board/ Communications
a) Brief Exco and Board on member and staff communication | 2020-03-18 | 2020-04-03 |  | Not Started
Management to write | 2020-03-18 | 2020-03-16 |  | Complete
GM to sign | 2020-03-18 | 2020-03-16 |  | Complete
b) Seek approval from Exco and/or board as needed | 2020-03-18 | 2020-04-03 |  | Not Started
c) Do we inform committee members of decisions prior to the entire membership? | 2020-03-18 | 2020-04-03 |  | Not Started
5. Committee Communication
a) Phone meetings scheduled | 2020-03-18 | 2020-04-03 |  | Not Started
b) Phone meetings cancelled / postponed | 2020-03-18 | 2020-04-03 |  | Not Started
c) Look into conference call solution for committees | 2020-03-18 | 2020-04-03 |  | Not Started
6. Other Stakeholder Communication
a) Schedule meetings with vendors | 2020-03-18 | 2020-04-03 |  | Not Started
b) Reach out to prospective members | 2020-03-18 | 2020-04-03 |  | Not Started
c) Group Reservations, special interest groups and other relevant stakeholders | 2020-03-18 | 2020-04-03 |  | Not Started
7. Member Offerings / venues
a) Short Term – now till April 1 | 2020-03-18 | 2020-04-03 |  | Not Started
Club closed | 2020-03-18 | 2020-04-03 |  | Not Started
Address pick up of clubs, wine, etc. | 2020-03-18 | 2020-04-03 |  | Not Started
b) Longer Term – After April 1 | 2020-03-18 | 2020-04-03 |  | Not Started
Easter alternative menu | 2020-03-18 | 2020-04-03 |  | Not Started
Dinner Alternative menu | 2020-03-18 | 2020-04-03 |  | Not Started
Leverage technology (app) | 2020-03-18 | 2020-04-03 |  | Not Started
Course Opening Plan – limited?? | 2020-03-18 | 2020-04-03 |  | Not Started
Committee Meetings | 2020-03-18 | 2020-04-03 |  | Not Started
Vendors | 2020-03-18 | 2020-04-03 |  | Not Started
Alcoholic liquor sales for off-premise consumption? | 2020-03-18 | 2020-04-03 |  | Not Started
8. Cleaning Action Steps
a) Non-Touch Hand Sanitizers will be added to the Clubhouse – | 2020-03-18 | 2020-04-03 |  | Not Started
b) Assigning Personnel to Clean | 2020-03-18 | 2020-04-03 |  | Not Started
Create cleaning checklists - MG | 2020-03-18 | 2020-04-03 |  | Not Started
To include all hard surfaces (knobs, handles, switches, counter-tops, touchscreens, etc.) | 2020-03-18 | 2020-04-03 |  | Not Started
c) Common Spaces - CLOSED | 2020-03-18 | 2020-04-03 |  | Not Started
9. Facility Plans – CLUB CLOSED till April 1
a) Clubhouse – CLOSED | 2020-03-18 | 2020-04-03 |  | Not Started
Function Changes
Policy Changes
Communications
b) Administrative Offices - CLOSED | 2020-03-18 | 2020-04-03 |  | Not Started
Function Changes
Policy Changes
Communications
c) Food & Beverage - CLOSED | 2020-03-18 | 2020-04-03 |  | Not Started
Function Changes
Policy Changes
Communications
d) Golf Courses - CLOSED | 2020-03-18 | 2020-04-03 |  | Not Started
Function Changes
Policy Changes
Communications
e) Golf Courses - CLOSED | 2020-03-18 | 2020-04-03 |  | Not Started
Function Changes
Policy Changes
Communications
f) Racquet Center - CLOSED | 2020-03-18 | 2020-04-03 |  | Not Started
Function Changes
Policy Changes
Communications
10. OTHER
a) Turf Maintenance Building | 2020-03-18 | 2020-04-03 |  | Not Started
b) Prospective Member Tours - Cancelled | 2020-03-18 | 2020-04-03 |  | Not Started
c) Committee Meetings | 2020-03-18 | 2020-04-03 |  | Not Started
TBD | 2020-03-18 | 2020-04-03 |  | Not Started
d) Group Business | 2020-03-18 | 2020-04-03 |  | Not Started
Catering to reach out and give opportunity to book later. | 2020-03-18 | 2020-04-03 |  | Not Started
No fees | 2020-03-18 | 2020-04-03 |  | Not Started
e) Guest Outings / Banquets | 2020-03-18 | 2020-04-03 |  | Not Started
Review contracts | 2020-03-18 | 2020-04-03 |  | Not Started
Investigate options | 2020-03-18 | 2020-04-03 |  | Not Started
Calculate net income for each to understand impact | 2020-03-18 | 2020-04-03 |  | Not Started
11. Staff policy / scheduling and pay scenarios
a) Short Term - Pay till April 7 | 2020-03-18 | 2020-04-03 |  | Not Started
A – policy and cost for total shutdown (till April)– current | 2020-03-18 | 2020-04-03 |  | Not Started
Salary. FT. PT . Seasonal | 2020-03-18 | 2020-04-03 |  | Not Started
b) Long Term | 2020-03-18 | 2020-04-03 |  | Not Started
B – policy and cost for total shutdown (till June 30 )– no member offerings | 2020-03-18 | 2020-04-03 |  | Not Started
C– policy and cost for partial shutdown (as of April 1) – F&B to go and limited golf ONLY | 2020-03-18 | 2020-04-03 |  | Not Started
12. Scenario Planning
a) Identifying scenarios for total and partial shutdown | 2020-03-18 | 2020-04-03 |  | Not Started
A – Total Club shutdown (current) till April 7 - Shelter in place | 2020-03-18 | 2020-04-03 |  | Not Started
B - Total Club shutdown till June 30 - Shelter in place | 2020-03-18 | 2020-04-03 |  | Not Started
C - Total Club shutdown till March 31, 2021 - Shelter in place | 2020-03-18 | 2020-04-03 |  | Not Started
D – Modified shutdown from April 7 till June 30 - | 2020-03-18 | 2020-04-03 |  | Not Started
E – Modified shutdown till March 31, 2021 | 2020-03-18 | 2020-04-03 |  | Not Started
b) Assumptions for scenario planning – need impact figures for each | 2020-03-18 | 2020-04-03 |  | Not Started
Assume no dues increase entire year – $ | 2020-03-18 | 2020-04-03 |  | Not Started
Assume no dues increase till June 30 – $ | 2020-03-18 | 2020-04-03 |  | Not Started
No wage increases for Leadership team as of April 1- $ | 2020-03-18 | 2020-04-03 |  | Not Started
No wage increases for Leadership team till June 30 - $ | 2020-03-18 | 2020-04-03 |  | Not Started
No wage increases for all salaried employees as of April 1- $ | 2020-03-18 | 2020-04-03 |  | Not Started
No wage increases for all salaried employees till June 30 - $ | 2020-03-18 | 2020-04-03 |  | Not Started
No wage increases for all as of April 1 - $ | 2020-03-18 | 2020-04-03 |  | Not Started
No wage increases for all till June 30 - $ | 2020-03-18 | 2020-04-03 |  | Not Started
Bonuses? | 2020-03-18 | 2020-04-03 |  | Not Started
13. Preserving Cash Plan
a) Review all Capital Projects (2020 & 2021) | 2020-03-18 | 2020-04-13 |  | Not Started
Identify and get my approval on what MUST be done now | 2020-03-18 | 2020-04-13 |  | Not Started
Provide revised special project list and capital required | 2020-03-18 | 2020-04-13 |  | Not Started
b) Reevaluate loan payment schedule | 2020-03-18 | 2020-04-13 |  | Not Started
Identify minimum payment schedule | 2020-03-18 | 2020-04-13 |  | Not Started
c) Consider drawing online of Credit | 2020-03-18 | 2020-04-13 |  | Not Started
Seek approval from board and Finance | 2020-03-18 | 2020-04-13 |  | Not Started
d) Forecast member resignations and impact on budget | 2020-03-18 | 2020-04-13 |  | Not Started
Senior members impact | 2020-03-18 | 2020-04-13 |  | Not Started
Membership Director document daily ins and outs of memberships | 2020-03-18 | 2020-04-13 |  | Not Started
What’s the trigger to introduce alternatives? | 2020-03-18 | 2020-04-13 |  | Not Started
e) Forecast new member assumptions | 2020-03-18 | 2020-04-13 |  | Not Started
Consider prospective incentives if necessary | 2020-03-18 | 2020-04-13 |  | Not Started
f) Investigate extending member payment schedule | 2020-03-18 | 2020-04-13 |  | Not Started
Extend payment due dates by one additional month | 2020-03-18 | 2020-04-13 |  | Not Started
What’s the trigger? | 2020-03-18 | 2020-04-13 |  | Not Started
g) Review all outside revenue bookings / reschedule | 2020-03-18 | 2020-04-13 |  | Not Started
Calculate net loss | 2020-03-18 | 2020-04-13 |  | Not Started
Review contracts for cancelations | 2020-03-18 | 2020-04-13 |  | Not Started
Consider alternative dates | 2020-03-18 | 2020-04-13 |  | Not Started
Develop policy and communication for cancellation / reschedule | 2020-03-18 | 2020-04-13 |  | Not Started
h) Review Weddings and Private Party List | 2020-03-18 | 2020-04-13 |  | Not Started
Develop list | 2020-03-18 | 2020-04-13 |  | Not Started
Calculate net impact | 2020-03-18 | 2020-04-13 |  | Not Started
i) No new contracts to be signed (even if prior approval | 2020-03-18 | 2020-04-13 |  | Not Started
14. Cost Cutting Plan
a) Payroll | 2020-03-18 | 2020-04-13 |  | Not Started
b) Expenses | 2020-03-18 | 2020-04-13 |  | Not Started
c) Interns | 2020-03-18 | 2020-04-13 |  | Not Started
d) Vendors | 2020-03-18 | 2020-04-13 |  | Not Started
e) Contracts | 2020-03-18 | 2020-04-13 |  | Not Started
f) Events | 2020-03-18 | 2020-04-13 |  | Not Started
15. Revenue Generation Plan
a) New Business Model | 2020-03-18 | 2020-04-13 |  | Not Started
b) Meal Replacement | 2020-03-18 | 2020-04-13 |  | Not Started
c) Butcher To Go | 2020-03-18 | 2020-04-13 |  | Not Started
d) BBQ To Go | 2020-03-18 | 2020-04-13 |  | Not Started
e) Food Truck / Private Event Catering | 2020-03-18 | 2020-04-13 |  | Not Started
f) One Stop Shop (Golf / Food / Valet and Car Wash etc…) | 2020-03-18 | 2020-04-13 |  | Not Started
g) Pantry offering | 2020-03-18 | 2020-04-13 |  | Not Started
h) Golf offering | 2020-03-18 | 2020-04-13 |  | Not Started
i) Other ideas?? | 2020-03-18 | 2020-04-13 |  | Not Started
16. Determine a plan for Shelter in Place – NO STAFF OR MEMBERS
a) Trigger - Order from City Officials | 2020-03-18 | 2020-03-19 |  | Not Started
b) Email all staff asking everyone to stay home for 14 days or until further notice | 2020-03-18 | 2020-03-19 |  | Not Started
c) Email members to inform them and provide information on what happens next in terms of communication if calling club | 2020-03-18 | 2020-03-19 |  | Not Started
d) Staff to develop TOTAL SHUTDOWN Plan and communication | 2020-03-18 | 2020-03-19 |  | Not Started
e) Identify company to clean club prior to reopening | 2020-03-18 | 2020-03-19 |  | Not Started
Vendors | 2020-03-18 | 2020-03-19 |  | Not Started
When to clean | 2020-03-18 | 2020-03-19 |  | Not Started
When to reopen | 2020-03-18 | 2020-03-19 |  | Not Started
17. Determine trigger and plan to close club completely – NO STAFF OR MEMBERS
a) Trigger - Shelter in place is extended OR a member or employee has been diagnosed and has been on property within 14 days | 2020-03-18 | 2020-04-05 |  | Not Started
b) Email all staff asking everyone to stay home for 14 days or until further notice | 2020-03-18 | 2020-04-05 |  | Not Started
c) Email members to inform them and provide information on what happens next in terms of communication if calling club | 2020-03-18 | 2020-04-05 |  | Not Started
d) Staff to implement TOTAL SHUTDOWN Plan and communication | 2020-03-18 | 2020-04-05 |  | Not Started
e) Identify company to clean club prior to reopening | 2020-03-18 | 2020-04-05 |  | Not Started
Vendors | 2020-03-18 | 2020-04-05 |  | Not Started
When to clean | 2020-03-18 | 2020-04-05 |  | Not Started
When to reopen | 2020-03-18 | 2020-04-05 |  | Not Started
18. Determine trigger and plan to reopen club completely – BUSINESS AS USUAL
a) Trigger - ? | 2020-03-18 | 2020-04-05 |  | Not Started
b) Leadership Team to develop “ramp up” plan | 2020-03-18 | 2020-04-05 |  | Not Started
Develop “back to work” protocol | 2020-03-18 | 2020-04-05 |  | Not Started
Temperature screening | 2020-03-18 | 2020-04-05 |  | Not Started
c) Email all staff asking everyone to return with schedules attached | 2020-03-18 | 2020-04-05 |  | Not Started
d) Email members to inform them and provide information on what happens next in terms of communication if calling club | 2020-03-18 | 2020-04-05 |  | Not Started
e) Publish schedule on web | 2020-03-18 | 2020-04-05 |  | Not Started
f) Revise club calendar and repost | 2020-03-18 | 2020-04-05 |  | Not Started
g) Staff to develop Business as Usual Plan and communication | 2020-03-18 | 2020-04-05 |  | Not Started
h) Identify resources needed prior to reopening | 2020-03-18 | 2020-04-05 |  | Not Started
Staff | 2020-03-18 | 2020-04-05 |  | Not Started
Vendors | 2020-03-18 | 2020-04-05 |  | Not Started
Equipment | 2020-03-18 | 2020-04-05 |  | Not Started
19. Club Events / Golf Tournament Status
a) Easter | 2020-03-18 | 2020-04-05 |  | Not Started
b) Aerification | 2020-03-18 | 2020-04-05 |  | Not Started
c) 9 Hole meet & Greet | 2020-03-18 | 2020-04-05 |  | Not Started
d) Golf Captain's Opening | 2020-03-18 | 2020-04-05 |  | Not Started
e) Mother's Day | 2020-03-18 | 2020-04-05 |  | Not Started